# DOMESTIC HOMICIDE REVIEW 5 - ACTION PLAN

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Recommendation** | **Activity/milestones** | **Target Date** | **Lead Agency** | **Outcome** | **Status** |
| 1 West Yorkshire Police ensures that all police officers and staff are reminded of the importance of making Adult Safeguarding notifications or referrals to Adult Social Care in circumstances where a Vulnerable Adult is known to be resident (full or part time) within an environment where domestic abuse is identified | Briefing item to be placed on the West Yorkshire Police internal website for the attention of all staff.Separate briefing item to be sent to all Detective Inspectors in the District Safeguarding Units for the attention of all the Safeguarding Staff | Briefing published 21/12/15All safeguarding DI’s notified 21/12/15 | WYP | Increased awareness of adult and dv safeguarding within WYP and high risk cases being filtered through CSU lead/MARAC processes. | Complete |
| 2 Tower Hamlets Community Safety Partnership provide an outline of the learning from this review, suitably anonymised, to promote further the encouragement of personal and third party reporting of domestic abuse within Tower Hamlets, specifically within the Somali community | * Key recommendations presented to CSP/VAWG Forum, DV Forum and NPFH Forum
* Delivery of VAWG/DV Training at Mosques
* Somali Taskforce Action Plan developed to include work around DV/VAWG
* Communications Team to undertake quarterly promotion of reporting options via range of mediums
* Review existing reporting options in the borough including project review of Third Party Reporting (TPR) Centres
* Undertake 10 outreach activities with wider communities to encourage reporting of VAWG/DA including recruitment of VAWG Champions
* Development of borough wide White Ribbon Campaign activities
* Engage with organisations working with Somali organisations encouraging participation and involvement in VAWG/DV agenda.
 | * 3/5/16
* August 2016
* December 2016
* December 2016
* October 2016
* September 2016
* December 2016
 | LBTH  | Increased awareness to encourage reporting of VAWG/DAIncreased understanding amongst those who live and work in the borough of VAWG/DA issues with over 50 activities taken place across DV and HC. Over 900 DV pledges signed in December 2016 for White Ribbon Campaign increasing awareness and engagement with wider communityTargeted support for under reported groups to encourage access to support and protection, particularly Somali community. Development and regular monitoring of Somali Taskforce Action Plan by lead members ensuring improved community engagement.TPR Report produced by MPS reviewing TPR. In response, more efficient and cost effective means of reporting in the borough have been promoted, including specialist organisations and reporting options aswell as the development of Queen Mary University and REAL as reporting centres. Key Somali organisations approached, training offered and invitations to participate in key forums. Commissioning of a VAWG specialist project to undertake outreach and consultation with Somali community.  | Complete |