## Schools
Schools Improvement Plan | [7 empty] | V1.1
|  | Improvement Plan Actions | Actions to date and comments | Responsible Officer | Interdepend-ancies | Resources | Target Date - RAG | Completion Date | Comments
2020/21 Process and Closure
| For 2020/21 the process for recording School transactions will not change as it is difficult to implement a new process mid way through the year | Document the process | Draft staus - being reviewed. PL note the VAT claim needs to be included | KG |  | Les Horsley/ Emdad Abul | 2021-03-15 |  |  | Notes from C4 Main Improvement plan
| Monthly reconciliation of School Returns including copies of bank reconciliation and budget monitoring statements. (PW recommendation) | See Improvement Plan - Schools finance team not resourced to do monthly reconciliations of schools returns. Look into RAG rating | See C4 in Improvement Plan | KG |  | KG | 31/10/21 for review |  | Review whether monthly reconciliations are required by 31/10/21 | The Council should aim to set up a monthly monitoring process whereby all schools provide copies of bank reconciliations and budget monitoring statements within 10 days of each month-end, and this information is used to confirm each schools’ cash balances, reserves balances and spend to date against DSG allocation. Journal postings can then be made on a regular basis throughout the year to eliminate internal transactions and recharges and post accurate figures for schools’ cash balances and reserves to the Balance Sheet. | The decision for the need to move to monthly monitoring for schools will be taken at the end of October 2021. A more robust quarterly monitoring process has been implemented as well as further improvements planned in for 2020/21. These include ensuring that DSG budget allocations are made through a monthly BACs payment set up at the beginning of the school year, internal payroll is posted directly, rather than as a year end process which can then be checked and monitored regularly. There is also a consideration to make service level agreement charges an annual in advance invoiced amount and for other school income payments to be made on a quarterly rather than monthly basis. There is a plan in place to record the bank balance more transparently on the ledger to ensure the bank account reconciliation is possible for the council in a simple form.
| Information from Schools | (i) Request for Budget Monitoring returns for Q3, plus bank reconciliation by 31st January. This will allow for early checks. | Requested, data starting to come in. Need to agree how to chase the rest next week (individual chase). Ahad will confirm the %. Next week, the review of the data will start, which is the big change. | KG |  | Suhal Kadir/ Almusur/ Mohammed Ahad | 2021-02-12
|  | (ii) Communication with Schools on Closure of Accounts deadlines for returns (e.g. accruals, bank reconciliation as at 31st March) | Meetings scheduled in - workshops held. Key dates in the workshops. | KG |  | KG/ Nikki Parsons | 2021-02-28
|  | (iii) Set up briefing and Training Schools for January and February 2021. | 5 workshops, last one day after half term. | KG |  | KG/ Nikki Parsons | 2021-02-28
| - Quality of Working Papers from Schools variable. - Need to produce YE guidance based on corporate guidance - | (iv)Issue Closure timetable for Schools (v) Provide example of Good working paper and supporting documentation required. | Holding meetings with School Business managers. Engaged with the planning for workshops stage to review the template, with the Chair of the Forum. One of the external consultants signed up for the workshops, the other yet to sign. Plan is to have an ongoing relationship with the 2 external consultants as they are key to getting the right quality. These 2 cover 35 or so schools. | KG |  | KG/ Nikki Parsons | 2021-01-31
| Payroll Posting Early Closure caused problems for internal payroll postings. External Payroll Obtaining information especially around external payroll proved difficult. | (i) Internal Payroll to be posted by 31/03/21 to ensure that no accruals are required. (ii) External Payroll - Early requests to Schools and External payroll providers for reports required. | Internla payroll - yes, meeting with DK was positive. External provider, NP has been contacted for the largest external provider. Last year, the request was unclear esp. re senior renumeration, so we need to make the form clearer (AK to do this). TH - there are a couple of academies (St Pauls) in the schools rev cost centres. Should not be on our ledger. We need to establish a BACs bureau to do that or we do not act as their payroll. | KG |  | Nikki Parsons/ Emdad Abul/ Damian Kennedy | 31/01/21 for comms
Schools Finance Activities for 2020/21
| Processing of School returns Schools are expected to make their final returns to the LA by 16th April | (i) Schedule in processing of returns. (see detail below on issues with journals previously) | Highlighted in the workshops. Put in our e mails to schools such as cash advances. Headteachers bulletin - will insert a reminder. | KG |  | Emdad Abul/ Mohammed Ahad | 2021-04-22
| Journal Processing | (i) Use correct coding for accruals in particular classifying internal and external debtors and creditors for schools and academies. (ii) Use correct coding for SLA journals (previously posted as income) (iii) ensure VAT is accounted for correctly on Academy invoices (iv) Keep creditor and debtor accrual journals separate when posting to Agresso with meaningful description on the text field to help when analysing reports for audit queries etc. (v) Have a peer review of accrual journals | The internal income is being cleansed as the wrong codes were being used, so all maintained income on its own code, so no inflating income. Service managers contacted to inform them of the code change. TH - there are some internal tranactions on a code for external - TH will run a report, it's school meals. This will need to be scutinised as this is an area that has gone wrong before re coding. NP will contact the person who codes this data. Won't be any year end accruals. | KG |  | Emdad Abul/ Mohammed Ahad | Ongoing |  | Ensure staff re aware of codes to use.
| Reconciliation of Disbursement Account (We do not hold individual School Bank Accounts on the balance sheet. | (i) All journals to related to School cash advances processed and up to date; (ii) Check for any backlog of journal processing; (iii) Schools Expenditure model produced (this includes the schools bank reconciliation and to tie back to the position on reserves and Reserves control account.) (iv) Chief Accountants Team to review reconciliation. | DDs for payroll and pensions being checked, review of any backlogs, all funding streams being checked. LH will be the reviewer, agreed with AK. | KG |  | Emdad Abul | 31/01/21 to 29th April
2021/22 Process
Payments to School - Schools are currently paid by CHAPS and then journals are processed to record against codes in Agresso. Improvesments to this process are to be implemented for 2021/22.
|  | (i) Check with Payments Team manager on how recurring payments and Ad hoc payments can be set up for Schools; (ii) Idenfify actions to set up recurring payments (iii) Set up individual school bank account codes on the balance Sheet with advice on code conventions for set up. (iv) Set up recurring payments schedule for the schools budget share. (v) Establish the process for adhoc payments (vi) First recurring payment to be made in April. | KG had inital meeting with Jo, Jo checking with the Agresso team. The first upload is 1st April. What is the methodology, this needs to be documented. DC will lead on this process change and documentation. | KG/ AK |  | Emdad Abul/ Jo Cambell Les Horseley jo Cambell KG/Les/Emdad Jo Cambell | 29/01/21 for initial assessment By 15/03/2021
Other
| CIES Review Grants Analysis was more difficult. Need for clear coding of grants - Actual grant amounts did not reconcile to GL postings as Cat code may have been missed. Historic Cat code description still against the Cat 5. E.g Standards Fund as a description. | (i) Record of Remittances and grants received saved in shared folder. (ii) Review coding of grants | DC has done the gtants register, reveiw of grant conditions, it's in hand, Ahad is working on this. | KG/ AK |  | Nikki Parsons | in readiness for grants note and audit sampling, end Feb
| Historic cash advances with Schools were not documented or payment plans set out. Currently Licensed Deficits not signed off | (i) Historic cash advances with repayment plans to be set agreed with schools. (ii) Licensed deficits to be agreed at the point of schools going into deficit with approval from Corporate Director of Childrens and Chief Finance Officer. (iii) Document process for current licensed deficits and new schools with deficits. | Sent e mails to confirm with schools, not all of them here. Next, need to confirm repayment plan, if necessary, put in writing where it has not been done. DC will lead on the documentation of this process. | KG |  | DC | 31/3/21
| Process Convoluted Process has historically worked, as the people in post knew the process, but not the most efficient process. Need to learn from what other LAs do as this is much simpler (A to B). The current process means that if something goes wrong it is difficult to unravel. | Do we need code BZ930? | Map process that will work for 2020/21. Map process for use from April 2021 as it would not be sensible to change mid year.
| Limited detail on text for accrual journals- made analysis of these journals time consuming. | Create journals with sufficient detail to inform what the accrual id for e.g. Catering SCR for maintained schools. Do not mix SDR and SCR journals on the same journal
| Coding Journals Correctly - Normal journals - Accruals coding is confusing (split between internal and external debtors). - Clarity on the DSG Codes | Ensure that correct codes are used for maintained and Academy schools. Correct coding for SLA journals Have a peer review of accruals
| Someone in Corporate centre be made responsible for all Bank Accounts | Need clarity on who will coordinate that bank reconciliations have been undertaken.
| Need for a Corporate Grants Register | Need to incorporate all Childrens related grants